## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
21-Feb-17 | 1 | Data sharing from BBSRI at risk | Technology Development | Technology Development | Environmental | 4 | 2 | Low | facilitate conversations with Umaine on data sharing | 3 | 1 | Low
21-Feb-17 | 2 | Ice data collection unsuccessful | Technology Development | Technology Development | Uaa Lead | 3 | 3 | Low | real time data collection implemented | 1 | 2 | Low
21-Feb-17 | 3 | Appropriate permits and licenses procured in time for open water testing | Technology Development | Planning | Environmental | 4 | 4 | Low | FERC Final license application submittal scheudled for 12/17 | 3 | 4 | Low
21-Feb-17 | 4 | Wet Gap Generator design not yet complete | Technology Development | Technology Development | Lead Engineer | 4 | 3 | Low | Design reviews and component validation testing | 2 | 3 | Low
21-Feb-17 | 5 | Timing of generator procurement from IKM could be tight for schedule | Technology Development | Procurement | Lead Engineer | 4 | 3 | Low | Ensure Generator delivery by 2/2018 to allow adequate time for testing using project development plan with regular status reports | 3 | 3 | Low
21-Feb-17 | 6 | components are not available | Procurement | Procurement | Lead Engineer | 2 | 2 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 1 | 3 | Low
21-Feb-17 | 7 | Fabricated components have significant lead times | Procurement | Procurement | Lead Engineer | 3 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 2 | 3 | Low
21-Feb-17 | 8 | Fabricated components have significant lead times | Procurement | Procurement | Lead Engineer | 4 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 2 | 3 | Low
21-Feb-17 | 9 | Singel source vendor for some components that require design completion and fabrication | Technology Development | Procurement | Project Management | 4 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip | 3 | 3 | Low
21-Feb-17 | 10 | components are not available, integration of components and software is delayed | Technology Development | Procurement | Lead Engineer | 4 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 3 | 3 | Low
21-Feb-17 | 11 | Fabrication delays and out of spec delivered product | Technology Development | Procurement | Project Management | 4 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 3 | 3 | Low
21-Feb-17 | 12 | components are not available | Procurement | Procurement | Lead Engineer | 3 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue | 1 | 3 | Low
21-Feb-17 | 13 | Custom components require fabrication lead time | Technology Development | Procurement | Lead Engineer | 4 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 2 | 3 | Low
21-Feb-17 | 14 | Custom components require fabrication lead time | Technology Development | Procurement | Lead Engineer | 4 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 2 | 3 | Low
21-Feb-17 | 15 | Custom components require fabrication lead time | Technology Development | Procurement | Lead Engineer | 4 | 3 | Low | Frequent vendor communication , issue PO with room for schedule creep, Rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery | 2 | 3 | Low
21-Feb-17 | 16 | Buoyancy System fails some or all of validation tests | Technology Development | Technology Development | Lead Engineer | 3 | 4 | Low | Utilizing Incremetnal improvements to a proven concept, add redundancy to design Perform land based tests in May 2017 and move on to on water validation tests prior to shipment to Igiugig | 2 | 3 | Low
21-Feb-17 | 17 | Sturctural Assembly fails some or all of validation tests | Technology Development | Technology Development | Lead Engineer | 3 | 4 | Low | FEA analysis of structure include load factors following DNV standards and considers extreme loading conditions such as uneven bottom and detalied CAD models for subsystem interfaces vlaidation tests to ensure strucutral integrityu meets specs incorporate structural redundancy | 2 | 3 | Low
21-Feb-17 | 18 | Turbine Assembly fails some or all of validation tests | Technology Development | Technology Development | Lead Engineer | 3 | 3 | Low | Utilize CFD as design tool for performance validation, FEA analysis of turbines include load factors following DNV standards and considers extreme loading conditions, secondary design input from composite manufacturer | 2 | 3 | Low
21-Feb-17 | 19 | Genertor fails some or all of validation tests | Technology Development | Technology Development | Lead Engineer | 4 | 3 | Low | Factory Accpetance testing and laboratory testing of Genertor integrated with Power elecrtornics to ensure compatibility | 2 | 3 | Low
21-Feb-17 | 20 | Power Electronics fails validation | Technology Development | Technology Development | Project Management | 4 | 3 | Low | Factory accpetance tests and sequenced laboratory testing to ensure Power Electronics meets requirements before shipment | 3 | 3 | Low
21-Feb-17 | 21 | SCADA system fails validation | Technology Development | Technology Development | Lead Engineer | 4 | 3 | Low | Factory accpetance tests and sequenced laboratory testing to ensure SCADA meets requirements before shipment | 3 | 3 | Low
21-Feb-17 | 22 | Power and data cables failure | Deployment | Deployment | Project Management | 3 | 4 | Low | Utilize proven cable technology utilize secondary cable armor in high risk areas utilize redundant conductors for data and fiber optic, reduce inspections and associated wear and tear | 2 | 4 | Low
21-Feb-17 | 23 | Mooring system failure | Deployment | Deployment | Lead Engineer | 3 | 5 | Low | Design to DNV standards, utilize geophyisical knowledge and seek industry expertise to specify mooring system components, consider most favorable failure modes | 2 | 5 | Low
21-Feb-17 | 24 | Driveline failure | Deployment | Technology Development | Lead Engineer | 4 | 4 | Low | Throught validation testing, desing system for increased operational tolerances and loads, choosed components with long service life and minimal maintenance and alignement requirements increase modularity for replacement | 3 | 4 | Low
21-Feb-17 | 25 | Mechanical Brake Failure | Deployment | Technology Development | Lead Engineer | 4 | 4 | Low | Throught validation testing, redundant electrical brake, Rely on third party expertise for design | 3 | 3 | Low
24-Feb-17 | 26 | Reciept of FERC Pilot license or permits are delayed and compromise deployment | Deployment | Regulatory | Environmental | 4 | 5 | Low | Continue regular dialogue with regulatory agencies after final pilot license and other permit applications, respond to AIRs in timely manner | 3 | 5 | Low
24-Feb-17 | 27 | Component shipment to Igiugig is delayed due to schedule slip, transportation contractor issues, weather or other | Procurement | Procurement | Project Management | 3 | 4 | Low | Track project schedule, align component validation and delivery to port of shipment with shipper schedules, ship components early if possible arrival on first barge of season (June 2018) or second (Jluy 2018) at latest | 2 | 4 | Low
24-Feb-17 | 28 | Device assembly difficult or requires modification in Igiugig | Technology Development | Technology Development | Lead Engineer | 3 | 4 | Low | Device assembly is fdifficult or requires workaround in Igiugig due to component interfaces, component damage during shipment, or other. Timing June-August 2018 | 2 | 4 | Low
24-Feb-17 | 29 | Power System deployment/comissioning encounters unexpected difficulties | Deployment | Execution | Project Management | 3 | 5 | Low | prior device testing and component testing in Nikiksi and elsewhere will reduce unexpected issues with deployment or comissioning. Thewe validation steps completed by May 2018 | 2 | 5 | Low
24-Feb-17 | 30 | Ice accumlation on or interaction with device causes power disruption, reduction, or equipment damage | Deployment | Operations | Lead Engineer | 4 | 5 | Low | Collection of in river ice data for 2 years prior to deployment feeds engineeering and IO&M planning, June 2017- June 2018. ON device ice monitoring allows for operational state modification if adverse conditions or interactions occure | 3 | 5 | Low
24-Feb-17 | 31 | Salmon smolt data collection shows adverse reaction, or inadequate data collection does not provide regualtory agencies with adequate information to allow operation or testing during salmon smolt outmigration | Technology Development | Environmental | Environmental | 4 | 4 | Low | Develop rigorous fish monitroing pland in budget period 2. Consulst with state and federal agencies reularly to ensure study plan and instrumentation provides adeqaute infoarmaton for decision making, operate device only under continuoius montiroring during smolt outmigration | 3 | 4 | Low
24-Feb-17 | 32 | Device removal complicated by technological or environmental factors | Deployment | Deployment | Project Management | 3 | 5 | Low | Buoyancy system includes redundant and isoalted retrieval mechanisms, pre testing In Nikiski to reduce risk of retreival issues arrising | 2 | 5 | Low
24-Feb-17 | 33 | Higher cost for maintenance and logistical support required for final design and operations plan, including training and personnel requirements, external equipment and spares. | Operations | Operations | Project Management | 4 | 4 | Low | Developing system requirements will be critical for determining technical scope for operations and maintenance technical support; involve local resources and include 3rd party input to accurately ascertain feasibility of proposed systems for logistical and technical requirements in remote environment. Develop trained leads during project who will be responsible for operating the systems after the project. | 2 | 2 | Low