## Sheet1
Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood No Action (1-5) | Impact No Action (1-5) | Risk Priority No Action (low, med, high) | Mitigating Action | Likelihood Current (1-5) | Impact Current (1-5) | Risk Priority Current (low, med, high)
1 | legislative changes | Ongoing |  | Head Of Legal Services | 5 | 5 | High | Use intelligence to Officers identify impending changes changes and their effects. The Council Register Ensure staff trained electronic and procedures and conducted ensure changed. with GDPR. Use professional The majority networking to identify best held with practice for and Council responding to change. All staff for further We respond to currently government consultations on The Council and each changes to GDPR legislation or policy to influence its development. | 5 | 2 | Med
2 | brexit | Ongoing |  | Head Of Corporate Services | 5 | 5 | High | Understanding and Government acting on passed intelligence from situation, LGA, CIPFA and hence other local The Council government take account sources. they emerge. The Council Identifying policies outcomes that require changing, their negotiations: effects and governance as Brexit effects start. The Council workforce workers; ensure The Council awareness information | 3 | 2 | Med
3 | failure of contractors and suppliers working on the council s behalf | Operations | Governance | Assistant Director (Corporate Management Team) | 4 | 4 | High | Regular monitoring The Leisure of contracts and 2018 performance by for contingency Managers. Potential Ensure that financial contracts have risk contracts registers and Individual mitigation in event contingency of contract failure. is part Service We are such recent We have to manage/monitor Grounds Service All other review ongoing The likelihood reduced established | 4 | 3 | Med
4 | failure of it systems | Operations | IT | Head Of IT And Digital Services | 5 | 5 | High | Effective auditing of GDPR systems and data held. An additional been Data backed-up securely off-site. The likelihood increased crime Regular penetration testing. The Council’s been Regular review of business continuity plans Disaster Recovery testing is undertaken at regular intervals | 3 | 4 | Med
5 | insufficient staff to provide council services insufficient leadership and or management capacity to deliver council priorities |  | HR | Chief Executive | 5 | 4 | High | Ensure all services All services have effective requirements Workforce plans ensure incorporated into establishment Service Plans, longer-term which ensure all work is prioritised Effective succession planning. Effective use of project management approaches/ principles when delivering priorities/ strategies | 3 | 2 | Med
6 | breach of ict security causes loss of service | Ongoing | IT | Head Of IT And Digital | 5 | 5 | High | Effective auditing of The Council systems and data Security held. helps threats. Data backed-up websites securely off-site. advised Council Regular penetration possible testing. processes made updated The likelihood increased crime | 3 | 4 | Med
7 | lack of access to council premises prevents services being delivered | Operations | Emergency Planning | Head Of Corporate Services | 5 | 5 | High | Regularly test Emergency Emergency Plan testing Test service Plans Business Continuity emergency Plans month. Improved Ensure key opportunities emergency planning staff attend regular liaison meetings a n d t r a in i n g P ro v i s io n o f ‘drop down’ facilities for staff | 3 | 2 | Med
8 | funding changes make council unsustainable | Ongoing | Finance | Head Of Finance | 5 | 5 | High | Using intelligence to We are model and plan for and the future changes and Term risks and move away balance from reliance on Govt reserves. funding to balance our budget. The Fair Retention Regular monitoring of and there current position and the Council’s reporting to Members. Council Workforce planning covers all scenarios. The Council Inclusion in national working groups, Commercialisation modelling and lobbying will enable for funding system after income. RSG ceases. Sharing Council’s Each Efficiency Plan with the opportunities and efficiency Government allows guaranteed multi-year grant settlement raising funding certainty. Shared services and partnership working | 3 | 3 | Med
9 | the council s ability to cope with a natural disaster | Ongoing Operations | Emergency Planning | Chief Executive | 4 | 5 | High | Regularly test Key senior Emergency Plan briefing Test Service Management Business Continuity test the Plans Recovery Ensure key Management emergency training planning staff Officers attend regular Recovery liaison meetings managers and training Local training Tactical The Council’s Plan have trained available. The Council Leisure The Council to be Council’s by the response | 4 | 4 | High
10 | major health and safety incident | Ongoing |  | Assistant Director (Corporate Services) | 4 | 4 | High | Ensure health and A thorough safety is standard Council agenda on all team carefully meetings. Programme Ensure equipment training inventory and Flu jabs inspections are up to date. Review Risk Assessments and Action Plans. Capture Port near misses and asses learning points | 3 | 4 | Med
11 | fraud and error committed against the council | Ongoing | Finance | Assistant Director (Finance) | 4 | 5 | High | Increase staff The Council vigilance National information Fraud awareness training for The Fraud Managers Partnership area, October Raise profile internally and Anti-Fraud externally for being successful prosecutions A fraud is currently The Council’s reviewed against 21) | 3 | 3 | Med
12 | failure of external investment institutions | Ongoing Operations | Finance | Investment Manager | 4 | 5 | High | Effective Treasury The Council’s Management regularly strategy. position. Robust auditing of The Treasury processes and considered policies. Updates half-yearly . | 4 | 2 | Med
13 | failure of governance in major partners or in the council as a result of partnership working | Ongoing | Governance | Head Of Governance And Partnerships | 5 | 4 | High | The Annual Assurance that to Corporate governance models correctly followed Council and in the Council’s interests. Scrutiny annual to ensure Support Members in arrangements governance of control. partnership bodies. . Internal Audit partnership arrangements. Ensure that the Council’s interests are protected as Members of the Combined Authority and as Officers working on joint projects. Ensure all Partners have robust Business Continuity Plans in place GDPR compliance Robust ICT governance processes | 3 | 3 | Med
14 | failure to achieve required savings targets | Ongoing | Financial | Chief Finance Officer | 5 | 4 | High | Robust control of Delivery corporate including Transformation Plan. Council’s financial Regular progress reports and Cabinet assurance to positive Members. Service transformation projects Commercialisation and Investment Strategy | 3 | 3 | Med
15 | over run of major council projects in time or cost | Ongoing | Financial | Chief Executive | 5 | 4 | High | Robust project Effective management. priority. Effective risk Major registers for projects. Cabinet Council | 2 | 3 | Med
16 | service provision affected by organisational change | Ongoing | Governance | Head Of Service Transformation | 5 | 4 | High | Business continuity Plans plans for each service. Services Plans Culture of Council lessons remains effective Workforce planning, All services Plans which includes succession All organisational planning for key senior roles an talent management ensure considered A comprehensive programme of management health surveillance changes/programmes. for groups of employees who The Council work in certain programme service areas (e.g. suite processes, refuse drivers, to help workshop, port and wellbeing, staff, etc.) Trained Mental Health First Aiders in place Stress awareness training Resilience training Staff engagement and consultation processes | 4 | 3 | Med
17 | political changes in national priorities | Ongoing |  | Head Of Policy And Partnerships | 4 | 5 | High | Understanding and The risks acting on result intelligence from process, LGA, CIPFA and as a risk other local government The recent sources. likelihood will continue Resources identified, approved and implemented without delay. Constant monitoring Horizon scanning via professional bodies Joint/collaborative working | 4 | 3 | Med
18 | capital funding strategy failure | Operations | Finance | Head Of Finance | 4 | 5 | High | Forward planning The Council’s and horizon regularly scanning. The current Regular high level borrowing monitoring of has been direction of travel and Financial mitigation required. Should capital Asset Management forecast, Plan. then the ensure Asset disposal strategy expenditure. Reviews available | 3 | 3 | Med
19 | poor communications with stakeholders | Operations | Governance | Head Of Communications | 5 | 4 | High | CSE Action Plan. The Council’s year by Staff survey. dedicated against Public consultations service on key issues. communication All change 3cs refresher project training communication stakeholders Team meetings “What’s Breaking” communication and “Horse’s Mouth” updates from the Chief Executive to all staff | 3 | 3 | Med
20 | commercial uncertainties associated with decisions taken as part of the council s commercial and investment strategy | Ongoing | Finance | Chief Finance Officer | 4 | 5 | High | All governance The Council’s requirements have reviewed been put in place and will be robustly This new reviewed going any new forward put in | 3 | 3 | Med